“We develop as we grow”

FINAL SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN

2011/2012

VISION OF THE MUNICIPALITY

An effective, efficient public institution delivering quality, sustainable services to better the lives of people

MISSION OF THE MUNICIPALITY

Bettering the lives of its communities through:

- Sustainable Services Delivery

- Provision of Sustainable Job Creation Opportunities

- Public Participation

SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN

The SDBIP provides the vital link between the Mayor, Council and the Administration, and facilitates the process of holding management accountable for its performance. The SDBIP is a management, implementation and monitoring tool that will assist the Mayor , Councillors, Municipal Manager, Senior Managers and Community. The SDBIP indicates the responsibilities and outputs for each of the senior managers in the top management team, the outputs to be used, and the time deadlines for each output. The SDBIP will therefore determine the performance agreement of the municipal manager and senior managers, including the outputs and deadlines for which they will be held responsible.

LEGISLATIVE REQUIREMENTS

In order to ensure good governance and accountability on the municipalities, the National Treasury, in terms of circular 13, indicates their preference for not prescribing other matters to be included in the SDBIP. However the following requirements remain imperative for compilation of the SDBIP:

- Revenue projection to be collected by revenue source

- Projection of expenditure (operating and capital)

- Quarterly projection of service delivery targets and performance indicators for each vote

- Ward information expenditure and service delivery

- Detailed capital works plan broken down by ward for a period of three years.

MUNICIPAL MANAGER’S PERFORMANCE SCORECARD

MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT

| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUNDING | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Performance Management System | To phase in the PMS to all municipal employees | Performance contracts signed with heads of sections | PMS | 20 PMS contracts signed | Council | R250 000 115/260458 | 30 Sept 2011 |  |  |  |
| Human Resources | To finalise the DWAE transfer of personnel into the Municipal Structure through the placement process. | An approved placement policy framework. | DWAE personnel placement. | 169 transferred employees placed. | Council | R30 000 115/260459 |  | 30 Dec 2011 |  |  |
|  | To compile and profile a comprehensive skills audit for officials and Councillors. | Analysis report of the skills gaps identified. | Training and Development | Skills gaps identified and training interventions planned and implemented. | Council & DWAE | R2,600,000 115/260300 |  |  |  | 30 June 2012 |
|  | To review the Work Place Skills Plan | Reviewed work place skills plan | Reviewing Workplace Skills Plan | WSP submitted to Council by 20 June 2012 and by 30 June 2010 to LGSETA |  |  |  |  |  | 30 June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUNDING | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
|  | To review the Employment Equity Plan of the Municipality | Employment Equity workshops conducted in the Municipality. | Employment Equity Plan reviewal | EE report submitted to Council by 21 Sept 2011 and to the Dept of Labour by 30 Sept 2011 | Council | R55,000 115/260297 | 30 Sept 2011 |  |  |  |
|  | To identify and attract potential and suitable bursary beneficiaries in the scarce skills category. | Bursaries awarded to deserving learners. | Bursary Scheme. | 8 bursars appointed and funded annually. | Council | R1,100,000 115/260305 |  |  |  | 31 March 2012 |
|  | To expose Municipal Bursary holders to practical work environment in the Municipality. | In-service training contracts signed with Bursary holders for December vacations and for third year learners. | Bursary Scheme In-service training | 10 bursars engaged in in-service training with contracts signed. | Council |  |  |  | 28 Feb 2012 |  |
|  | To exercise conferred powers and functions. | Developed by-laws and consulted and passed for enforcement. | Development of By-laws. | By-laws developed and approved as well as gazetted (4). | Council | R50,000 115/260560 |  | 31 Oct 2011 |  |  |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUNDING | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
|  | To develop outstanding HR policies | No. of HR Policies developed | HR Policy Development | 6 HR Policies and approved | Council | R50,000 |  |  | 31 March 2012 |  |
|  | To monitor the implementation of an HRD Strategy of the Municipality. | Human Resource Development Strategy | HRD Strategy | Implementation of the HRD Strategy | Council | R50,000 115/260296 | Ongoing | Ongoing | Ongoing | 30 June 2012 |
|  | To implement the job Evaluation and benchmarking process outcomes in line with the JE results by the National JE Moderation Committee. | Benchmarking process results | Implementing job evaluation and Benchmarking | Implementation of the JE Results. | Council | R2,000,000 115/203085 |  |  |  | 30 June 2012 |
|  | To implement internship programme | Number of selected candidates for internship | Implementing Internship programme | 6 Learners engaged on Internship Programme (IT & Finance) | LGSETA & Council | R264,000 |  |  |  | 30 June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUNDING | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
|  | To promote OHS practices | OHS compliance measures implemented | Occupational Health & Safety | No. of Health & Safety cases reported and attended to. | Council | R200,000 115/260294 |  |  |  | 30 June 2012 |
|  | To develop and implement the municipal EAP | EAP Policy Developed and Implemented to assist Council employees on wellness issues | Employee assistance program | 20 employees receiving employee assistance from the Municipality | Council | R77,000 115/260295 |  | 31 Dec 2011 |  |  |
|  | Standardization of compilation of agendas for Council committees | Manual on compilation of agendas compiled and approved by council | To develop a manual for compilation of agendas | 1 manual compiled | Council |  |  | 30 Oct 2011 |  |  |
|  | Submission of 2011/12 Council resolution implementation report | Number of Council resolution implementation reports | Council Resolution monitoring | 1 quarterly report compiled per quarter | Council |  | 30 Sept 2011 | 31 Dec 2011 | 31 March 2012 | 30 June 2012 |
|  | Review of delegation of powers | Completion of Delegation review | Reviewed and approved System of Delegations | 1 |  |  | 30 Sept 2011 |  |  |  |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUNDING | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
|  | Review of Council standing rules and orders | Completion of the review process | Standing Rules and Orders adopted by Council | 1 |  |  | 30 Sept 2011 |  |  | 30 June 2012 |
| RECORDS MANAGEMENT | To promote administrative process through records management | Establishment of records office | To identify and equip the records office. compliance to National Archives Act. compliance to National Archives Act. Attend workshops on records management Purchasing of filing cabinets. Development of a File plan. Submission of a file plan to council committees for approval. Submission of a file plan to provincial Archivist for approval. Development of a registry policy. Development of a registry procedure manual. Centralize fax Procure stationery for registry office. | 1 central registry | Council | R60 000 130/260490 |  | 31 Dec 2011 |  | 30 June 2012 |
|  | To foster a sound labour relation with organised labour | Number of Local Labour Forum meetings held | A sound relation with organised labour | 12 LLF meetings | Council |  | Ongoing | Ongoing | Ongoing | 30 June 2012 |
|  | To report on all Council operations | Annual Report | Reporting on all Council operations | 1 Annual Report Adopted by Council | Council |  |  |  | 31 Jan 2011 (Draft) 31 March 2012 (Final) |  |

LOCAL ECONOMIC DEVELOPMENT AND TOURISM DEVELOPMENT

| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUNDING | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Continuous marketing of locally produced/manufactured product which also include cultural | Business exhibitions and entertainment show | Business development show Development and implementation of the LM Marketing Strategy | Increase by 40% the number of businesses showcasing their wares at the show from 43 to 60 and inclusion of the show as part of the municipal communication strategy | Council | R3,300,000 116/260016 | Ongoing | Ongoing | 31 March 2012 (Show) | Ongoing |
|  | To co-ordinate the promotion and marketing of local businesses | Business expansion and development | Business & tourist Guide brochure | Printing of 60 000 directory booklet | DEDET | R100,000 (DEDET MANAGED) | 30 Sept 2011 |  |  | 30 June 2012 |
|  | Sound management and institutional for the functioning of Nature Reserves | Conservation stewardship and environmental education programmes, mountain biking route, tourism accommodation. | Feasibility study for the development of the Mkhombo and Mdala Nature Reserve | Fully operation Nature reserves | Council/IDC | R500,000 504/306701 |  | 31 Dec 2011 |  |  |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUNDING | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| IDP | Address community need through developmental spatial & integrated planning | IDP Reviewed Draft by 31 January 2012 and final document by 31 March 2012 | IDP Review 2011/12 | IDP document adopted by 31 March 2012 | Council | R1,980,000 116/260520 |  |  | 31 March 2012 |  |
| OPMS | The development of the organisational performance management system addressing organisational challenges and needs | Operational OPMS document | OPMS Reports | Fully comply with Section 46 of MSA, MFMA | Council | R 220 000 116/260458 | Ongoing | Ongoing | Ongoing | 30 June 2012 |

MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT

| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUNDING | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Budget | To consult with community on adopted draft budget | 6 consultation meetings | Budget Consulting meetings | 31 wards | Council | R350 000 200/260005 |  |  |  | 30 April 2012 |
|  | To review budget related policies | Proper reviewed policies | Reviewing budget related policies | 7 policies | Council | R350 000 200/260005 |  |  |  | 30 April 2012 |
| Expenditure | To compile Annual Financial Statement | Annual Financial Statement | Compilation of Annual Financial Statement | Financial Statement 2010/2011 | Council | R300 000 200/260005 | 31 Aug 2011 |  |  |  |
|  | To upgrade cash management system | Upgraded cash management system | Upgrading cash management system | Upgraded system | Council | R50 000 200/ 260005 | 30 September 2011 |  |  |  |
|  | To ensure proper expenditure, monitoring and control | Quarterly financial statements | Monthly financial reports | 4 quarterly reports | Council | R150 000 200/260005 | 30 Sept 2011 | 31 Dec 2011 | 31 March 2012 | 30June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| Revenue | To construct new pay points and maintain existing ones | No. Of Pay-points constructed and maintained | Construction of pay points and maintenance of existing ones | 5 Pay points | Council | R2,750,000 203/306192 |  | 250 000 Advertisement of the Tender | 1 750 000 Appointment of the service provider | 750 000 The maintenance of the pay-points |
| Revenue | To procure programmable bulk water meters & activation hereof in big businesses & Government Departments Activation of water meters in Siyabuswa A, Libangeni & Digwale) | Increase of the revenue base & ability to restrict water live on the billing system | Procurement of programmable water metres | Installation of programmable water meters in big businesses & government departments Activating water meters 3 villages i.e Siyabuswa, Libangeni & Digwale | Council | R2,200,000 203/306185 R2,000,000 203/306185 | R200,000 Advertisement of the Tender | R1’600,000 Procurement of the water meters | 400 000 Procurement of the other meters 31 March 2012 | 30 June 2012 |
|  | Request Bulk Deeds Search from Deeds Office and Implement the MPRA in Napier and Ga-Mmakola Township | Bulk Deeds document /File from the Deeds Office and the Rates Reconciliation Register | Proper levying of the Rates accounts | (June-2012) All properties which are registered within Dr J S Moroka Municipality should be obtained | Council |  |  |  |  | 30 June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| Supply chain | To workshop service providers on bidding processes | No. Of Service providers workshopped on Procurement processes | Workshopping service providers on bidding processes | 85 service providers trained 2010/2011 | Council | R100,000 202/260280 |  | 31 March 2012 |  |  |
|  | Strengthening of the SCM Unit | Erection of new and secured tender box | Erection of new tender box and placement inside the LM building | One safe tender box | Council |  | 30 Sept 2011 |  |  |  |

GOVERNANCE AND PUBLIC PARTICIPATION

| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DISASTER MANAGEMENT | To educate community about disaster management | 4 Campaigns launched in the LM area | Conduct Awareness campaigns | 4 awareness campaigns in any 4 municipal wards in the 3 magisterial districts | Council | R400,000 Vote 162/260025 | 30 Sept 2011 | 31 Dec 2011 | 31 March 2012 | 30 June 2012 |
|  | To provide relief material to the communities | Provide temporary shelter and blankets | Procurement of shacks and blankets | 100 blankets and shelters procured as and when required | Council | R500,000 Vote 162/260025 | 30 Sept 2011 R125,000 | 31 Dec 2011 R125,000 | 31 March 2012 R125,000 | 30 June 2012 R125,000 |
| Waste Management | To procure protective clothing for staff | Staff allocated with protective clothing | Procurement of protective clothing | 1 Uniform procured for all staff members | Council | R400 000 Vote 520/260200 |  |  |  | 30 June 2012 |
|  | To provide an efficient and sustainable waste removal services | Reduction in littering and illegal dumping sites | Sustain food for waste project | Door to door Waste collection done at Libangeni and Siyabuswa | Council | R400 000 Vote 520/260024 | 30 Sept 2011 | 31 Dec 2011 | 30 March 2012 | 30 June 2012 |
|  | To educate communities on proper waste management strategies | Minimal illegal disposal of waste | Introduce the drama projects in educating communities | 4 awareness campaigns in 4 municipal wards | Council | R100 000 Vote 520/260024 | 30 Sept 2011 | 31 Dec 2011 | 30 March 2012 | 30 June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
|  | To rehabilitate the illegal dump sites | Parks developed on illegal dumping sites and open spaces | Develop 31 parks (1 in each ward) | Illegal dumping sites at Libangeni and Siyabuswa to be rehabilitated | Council | R1,5M Vote 520/260024 | 30 Sept 2011 | 31 Dec 2011 | 30 March 2012 | 30 June 2012 |
|  | To improve service delivery in waste management | Provision of a sustainable service | Procurement of 1refuse removal truck | Procurement of a refuse removal truck | Council | R1,5M Vote 520/306036 |  |  |  | 30 June 2012 |
| Cemeteries | To provide communities with easy identification to the graves | Speedy location of graves | Numbering of graves | Grave yards in all villages | Council | R1,M Vote 505/306036 |  |  |  | 30 June 2012 |
|  | To provide a service for pauper burials to the community of LM | Pauper burials done as requested by Government Mortuary | Provide pauper burial as and when required | Dignified burial Service provided to all paupers | Council | R50,000 Vote 505/260030 | 30 Sept 2011 | 31 Dec 2011 | 30 March 2012 | 30 June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| Traffic and Road Safety | To create a road safety environment to reduce accidents and to improve revenue collection | Conduct roadblocks during peak seasons, procurement of road safety/traffic equipments, issuing of traffic fines and execution of warrants of arrest | Effective traffic law enforcement conducting of road blocks | Conducting road blocks To improve revenue collection. Procurement of equipments | Council Council Council | R300,000 160/260331 R410.000 160/306057 |  |  |  |  |
|  | Improve road safety awareness/education | Conduct road safety promotion | Conduct road safety campaigns and scholar patrols conduct annual local road safety summit | Conduct 2 road safety awareness pre- Easter holidays and pre- festive season, Conduct 1 local road safety summit, improve road safety at schools and promote a road safety environment | Council | R300.000 Vote 160/260331 |  |  |  | 30 June 2012 |
|  | To protect municipal assets | Controlled access & protection of municipal assets | managing of security services | All municipal assets safeguarded | Council | R 9 M Vote 160/260430 | 30 Sept 2011 | 31 Dec 2011 | 30 March 2012 | 30 June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| Licensing/ Registering authorities | Enhance revenue collection | Revenue collected | Testing applicants for learners licences | 3600 applicants tested | Council |  | 900 learners tested | 900 learners tested | 900 learners tested | 900 learners tested |
|  |  |  | Testing applicants for drivers licenses | 5280 applicants tested for drivers licenses | Council |  | 1320 Applicants tested for drivers licenses | 1320 Applicants tested for drivers licenses | 1320 Applicants tested for drivers licenses | 1320 Applicants tested for drivers licenses |
|  |  |  | Registration and licensing of motor vehicles | Licensing of 8000 vehicles | Council |  | Licensing of 2000 vehicles | Licensing of 2000 vehicles | Licensing of 2000 vehicles | Licensing of 2000 vehicles |
|  |  |  | Testing of motor vehicles for roadworthiness | 1000 vehicles tested for roadworthiness | Council |  | 250 vehicles tested for roadworthiness | 250 vehicles tested for roadworthiness | 250 vehicles tested for roadworthiness | 250 vehicles tested for roadworthiness |
| Fleet Management | To register vehicles with the licensing authority | Licensed vehicles | Renewal of motor vehicle licenses | All municipal fleet registered | Council | R50 000 Vote 163/260210 |  |  |  | 30 June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| Arts and Culture | To promote heritage in all cultural groups | Provide donations to commemorate heritage days | Assist tribal authorities with funding | All council approved tribal Authorities to be assisted | Council | R650 000 Vote 166/260615 |  |  |  | 30 June 2012 |
|  | To promote and encourage communities to engage in Arts activities | Hold 1 Arts & Culture Festival | 1 Arts & culture festival to be held | 1 Arts festival in the Municipality | Council | R400 000 Vote 166/260616 | 30 September 2011 |  |  |  |
| LIBRARIES | To promote reading culture | Development of youth | Conduct reading programs competitions | 4 primary schools’ programmes | Council | R50 000 Vote 230/260451 | 30 Sept 2011 | 31 Dec 2011 | 30 March 2012 | 30 June 2012 |
|  | To improve the book collection | New books purchased for libraries | Current book sources provided to library users | 4 libraries stocked with additional books | Council | R50 000 Vote 230/260451 | 30 Sept 2011 | 31 Dec 2011 | 30 March 2012 | 30 June 2012 |
| FACILITIES | To purchase furniture for community halls | Buy additional Chairs and tables for halls | Chairs and tables to be bought | Chairs and tables bought |  | R26 000 Vote 300/306050 |  |  |  | 30 June 2012 |
|  | To upgrade the current state of facilities within the Municipality | Renovation of facilities | Facilities maintained | Maintenance and renovation of facilities |  | R3,8M Vote 300/235040 |  |  |  | 30 June 2012 |

BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT

| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BASIC SERVICE DELIVERY INFRASTRUCTURE | To ensure that all residents and road users have a safe and reliable roads and storm water drainage | The Public roads that are accident & dust free, smooth textured, drivable and surfaced | Implementation of all the funded roads and storm water projects as contained in the approved IDP for 2010/2011 | Servicing of 31 wards | Council & MIG | R75,3 M | Tender Stage | Construction | Completion of Construction | Overall Project’s Performance Evaluation |
|  | To provide bulk water & reticulation to households within Dr JS Moroka Municipality | Bulk water & reticulation | Implementation of all funded water projects as contained in the approved IDP for 2011/2012 | 14 wards serviced | MIG | R34,5 M | Tender Stage | Construction | Completion of Construction | Overall Project’s Performance Evaluation |
|  | To provide Sanitation to households within Dr JS Moroka Municipality | VIP Toilets | Implementation of all the funded sanitation projects as contained in the approved IDP for 2011/2012 | 14 wards serviced | MIG | R22 M | Tender Stage | Construction | Completion of Construction | Overall Project’s Performance Evaluation |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER |
|  | To upgrade facilities for sports, recreational and other purposes | Upgraded facilities | Implementation of all the funded facilities projects as contained inthe approved IDP for 2011/2012 | 3 upgraded facilities | Council & MIG | R23M | Tender Stage | Construction | Completion of Construction | Overall Project’s Performance Evaluation |
|  | To install high mast lights | High mast light | Implementation of all the funded electricity projects as contained in the approved IDP for 2011/2012 | 13 wards serviced | MIG | R14,3 M | Tender Stage | Construction | Completion of Construction | Overall Project’s Performance Evaluation |
|  | To refurbish bulk water pipeline, & pump station | Refurbished bulk water pipeline, & pump station | Refurbishment bulk water pipeline, & pump station | Reduction of water losses up to 10% in LM area | Council | R29,327,000 | Tender Stage | Construction | Completion of Construction | Overall Project’s Performance Evaluation |
|  | To improve the internal roads conditions through regravelling and routine maintenance | 800 km of roads gravelled | Roads regravelling programme | 31 Wards serviced | Council | R12,5 M | Tender Stage | Construction | Completion of Construction | Overall Project’s Performance Evaluation |

SPECIAL FOCUS: TRANSVERSAL AND YOUTH DEVELOPMENT

| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Transversal | To encourage culture of community building in communities To encourage elderly people to live a positive lifestyle | No. Of elderly people participating in community building activities | Nelson Mandela Day Painting of various schools/facilities by members of the community and Council One Elderly Summit | 3 Facilities in the three magisterial areas | Council | R2,300,000 | 20 July 2011 30 July 2011 |  |  |  |
|  | To encourage women to participate in all sporting codes | 10 soccer teams registered municipal sport council and attendance register | Soccer game, 15 kilometres marathon | 100 women playing soccer & 300 for marathon | Council | Refer to budget allocation above | 31 Aug 2011 |  |  |  |
|  | To empower women on governance issues | Establishment of women council | Women Parliament | 62 women participants | Council | Refer to budget allocation above | 31 August 2011 |  |  |  |
|  | To coordinate with the department of Social Services the hosting of meetings on child headed families & single parent headed ones | No. Of meetings held on Child headed families and single parent headed ones | World AIDS Day Commemoration the relaunch of the Dr JS Moroka Local Municipality LAC | 100 participants | Council | Refer to budget allocation above |  | 1 Dec 2011 | 31 March 2012 | 30 June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
|  | Women to be more organised and be able to be self sufficient, socially and economically | 150 women participating in the summit | Women summit | 150 participants | Council | Refer to budget allocation above | 31 Aug 2011 |  |  |  |
|  | To encourage culture of teaching and learning | No. Of attendees in the ECD process | ECD awareness and awards | 10 winners | Council | Refer to budget allocation above |  | 31 October 2011 |  |  |
|  | Promotion of the rights of children | Reduction of children abuse and attendance register | Children rights campaign | 300 children | Council | Refer to budget allocation above |  |  |  | 31 May 2012 |
|  | To coordinate with the department of Social Services, CDW’S & Home Based Care Organizations the destigmatisation of disability | 300 participants in the disability campaign | Disability campaign | 300 participants | Council | Refer to budget allocation above |  | 31 Dec 2011 |  |  |
|  | Reduction of illiteracy for People with Disability | Certificates for participants in the literacy campaign | Disabled skills development (Computer literacy and switchboard operating) | 30 participant | Council | Refer to budget allocation above |  | Recruitment | 31 January 2012 |  |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
|  | To encourage children to participate in debate about issues affecting them as informed by national and provincial programmes | Children rights awareness | Children Summit | 300 children | Council | Refer to budget allocation above |  |  |  | 30 June 2012 |
| YOUTH | To assist learners with correct career pathing | Assisting 300 learners with correct career pathing | Career Expo | 300 learners | Council | R 90 000 118/260578 |  |  |  | 30 June 2012 |
|  | Nurturing and encouraging youth to participation in sports, recreation, art and culture | Talent search through music, art and culture | Sports, Recreation, are and culture activities | 20 youth to be trained | Council | R155,000 118/260578 |  |  | May 2012 |  |
|  | Learners to be encouraged to participate in municipal operation | Youth parliament | 60 learners should have a clear understanding of the municipal operation | 60 learners annually should have a clear understanding of the municipal operation, politics and IDP. | Council | R100,000 118/260578 |  |  |  | 30 June 2012 |
|  | Entrepreneurship and skill development | Youth empowerment | Training that will empower co-operatives and out of school | 20 co-operatives to be trained and out of school youth for skill development | Council | R500,000 118/260578 |  |  | March 2012 |  |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
| YOUTH | Youth in Business and Art To encourage the education elite from the LM area to invest in kind to the skills depth of the municipality | Youth awards Education Indaba held | Encouraging youth organisation to participate in development of youth in economic, art, craft & health care awards One education indaba held | 30 youth organisation to participate in economic, art, craft & health care awards 100 participants to participate in the education indaba | Council Council | R900,000 118/260578 |  |  |  | 30 June 2012 30 June 2012 |
|  | Information from various department to assist with youth empowerment and review resolution of summit / indaba | Youth summit / indaba | 300 youth participating to be well informed to empower themselves | 300 youth to participating to be well informed to empower themselves | Council | R350,000 118/260578 |  |  |  | 30 June 2012 |
| KEY PERFOMANCE AREA | DEVELOPMENTAL OBJECTIVES | KEY PERFORMANCE INDICATOR | PROJECT | ANNUAL TARGET | SOURCE OF FUND | BUDGET | 1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARETR |
|  | Promoting sports participation within community and municipal officials | Sports summit / Indaba | Formulation of all association and be trained on their operation | 6 sporting codes should be formulated and be trained on their operation | Council | R670,000 118/260612 |  | 30 Sept 2011 | March 2012 | 30 June 2012 |

BUDGET 2011/2012

The following set of graphs gives an overview of the Municipal Budget for the financial year 2011/2012

BUDGET IS FUNDED FROM THE FOLLOWING SOURCES

| SOURCE OF FUND | ALLOCATION |
| --- | --- |
| EQUITABLE SHARE | 205,518,000 |
| FMG | 1,250,000 |
| MSIG | 790,000 |
| DWAF | 40,800,000 |
| MIG | 91,300,000 |
| COUNCIL FUNDS | 276,918,419 |
| IDC | 500,000 |

The below tables indicates the projected revenue by source and Operational Expenditure by type

|  | Medium Term Revenue and Expenditure framework |  |  |
| --- | --- | --- | --- |
|  | Budget Year | Budget Year +1 | Budget Year + 2 |
| REVENUE BY SOURCE | 2011/2012 | 2012/2013 | 2013/2014 |
|  | Budget | Budget | Budget |
| HOUSING | 1,500,000 | 1,650,000 | 1,815,000 |
| RATES & TAXES | 720,000 | 792,000 | 871,200 |
| CEMETARY | 140,000 | 154,000 | 169,400 |
| WATER & SANITATION | 38,355,400 | 42,190,940 | 46,410,034 |
| REFUSE | 4,450,000 | 4,895,000 | 5,384,500 |
| LIBRARY | 55,000 | 60,500 | 66,550 |
| RENTAL OF FACILITIES | 190,000 | 209,000 | 229,900 |
| INTEREST EARNED | 17,600,000 | 19,360,000 | 21,296,000 |
| TRAFFIC FINES | 350,000 | 385,000 | 423,500 |
| MOTOR LICENCING | 4,500,000 | 4,950,000 | 5,445,000 |
| GOVERNMENT GRANT | 225,016,000 | 247,517,600 | 272,269,360 |
| OTHER REVENUE | 7,000,000 | 7,700,000 | 8,470,000 |
| TOTAL REVENUE BY SOURCE | 299,876,400 | 329,864,040 | 362,850,444 |

OPERATING EXPENDITURE BY TYPE

Medium Term Revenue and Expenditure framework

| OPERATING EXPENDITURE BY TYPE | Budget Year 2011/2012 | Budget Year +1 2012/2013 | Budget Year + 2 2013/2014 |
| --- | --- | --- | --- |
| EMPLOYEE RELATED COST | 135,730,794 | 147,084,883 | 161,793,371 |
| GENERAL EXPENSES | 122,379,330 | 178,233,363 | 196,056,699 |
| REPAIR AND MAINTANCE | 51,105,295 | 54,173,125 | 59,590,437 |
| PROVISIONS AND RESERVE | 48,700,000 | 26,070,000 | 28,677,000 |
| CONTRIBUTION TO CAPITAL | 44,261,000 | 48,214,100 | 53,035,510 |
| TOTAL OPERATING EXPENDITURE | 402,176,419 | 453,775,471 | 499,153,018 |

The below graph illustrate the OPEX by type

PROJECTION OF OPERATING EXPENDITURE

CAPITAL EXPENDITURE BY TYPE

Medium Term Revenue and Expenditure framework

| CAPITAL EXPENDITURE BY VOTE | Budget Year 2011/2012 | Budget Year +1 2012/2013 | Budget Year + 2 2013/2014 |
| --- | --- | --- | --- |
| MUNICIPAL FACILITIES | 23,000,000 | 20,500,000 | 16,000,000 |
| ROADS & STORMWATER | 75,300,000 | 69,000,000 | 27,500,000 |
| SANITATION | 22,000,000 | 24,500,000 | 32,000,000 |
| WATER | 75,300,000 | 52,000,000 | 52,000,000 |
| ELECTRICITY | 14,300,000 | 7,500,000 | 0 |
| LED | 5,000,000 | 4,500,000 | 2,000,000 |
| TOTAL OPERATING EXPENDITURE | 214,900,000 | 178,000,000 | 130,000,000 |

Below graph illustrate the OPEX per vote

PROJECTION OF CAPITAL EXPENDITURE

BELOW TABLE SHOWS THE DETAILED CAPITAL PLAN